{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"external_links":2,"defined_names":3},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":67,"n_cols":7,"rows_kept":67,"merged":[[0,0,0,6],[1,0,1,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,3,6],[6,2,7,2],[13,2,15,2],[16,2,18,2],[21,2,23,2],[24,2,26,2],[27,2,29,2],[31,2,33,2],[34,2,35,2],[36,2,38,2],[39,2,40,2],[41,2,45,2],[46,2,50,2],[52,2,53,2],[55,2,57,2],[58,2,60,2],[61,2,63,2],[64,2,66,2]],"flags":["formulas_cached_only"]}
["2022年涉农统筹整合资金项目完成情况统计表"]
["填报时间：2022年12月1日           单位：万元"]
["序号","项目名称","责任单位","年度资金计划","已下达计划","开工\n情况","项目进展情况"]
[]
["合计",null,null,57466.347799999996,53435.591199999995]
[1,"大安市两家子镇万头肉牛养殖建设项目","畜牧业管理局",12600,12600,"已开工","正在施工，工程形象进度80%，目前6栋牛舍已建设完成，养殖基础母牛3517头。剩余15栋牛舍，其中12栋牛舍基础已经完成，6栋牛舍正在陆续安装钢结构。宿舍正在装修墙面，厂区外网基础施工，下一步准备安装牛舍内电器。消防水池正在安装内部系统。未建设的3栋牛舍计划2023年施工建设。"]
[2,"大安市45MW“新能源乡村振兴工程”项目","发展和改革局",3619.6,2000,"已完工","该项目工程已完工，正在准备并网。"]
[3,"国家农业产业融合发展示范园基础设施项目",null,750,750,"已完工","该项目工程已完工，正在准备验收手续。"]
[4,"大安灌区计量设施建设工程","灌区管理局",300,300,"已开工","正在施工，工程形象进度30%，目前设备陆续进场。预计2023年4月20日供水前安装调试完成。"]
[5,"大安市查干湖周边村屯生态修复项目","环保局",1026,1026,"已完工","该项目已完工。"]
[6,"大安市农村公路建设项目","交通运输局",10040,10040,"已完工","该项目已完工。"]
[7,"四棵树乡产业融合发展孵化园区建设项目","经济开发区",5000,5000,"已完工","该项目已完工。"]
[8,"大安市国有林场樟子松嫁接红松示范项目","林草局",165,null,"已开工","正在施工，工程形象进度65%，预计12月20日全部完工。"]
[9,"大安市2022年庭院经济建设项目","农业农村局",1600,1517.5536,"已完工","该项目已完工，已向市里提交奖补资金申请。"]
[10,"大安市白羽肉鸡现代农业产业园燃气管网建设工程",null,360,null,"已开工","正在施工，工程形象进度75%，预计12月末完工。"]
[11,"农村改厕建设项目",null,1200,null,"已完工","该项目已完工。"]
[12,"大安市2022年农村饮水安全巩固提升工程","水利局",994,994,"已完工","该项目已完工。"]
[13,"大安市农村饮水安全巩固提升工程（大岗子镇水厂项目）",null,1375,1375,"已开工","正在施工，工程形象进度94%，截至目前，设备已到位，正在进行设备安装调试，计划12月末完工通水。"]
[14,"大安市烧锅镇乡富田村机井配套工程",null,166.4,166.4,"已完工","该项目已完工。"]
[15,"月亮泡生态渔业工程建设项目","月亮泡渔场",1300,1300,"已开工","正在施工，工程形象进度70%，第三批鱼苗已投放完毕。预计2023年4月末全部完工。"]
[16,"农村危房改造项目","住建局",249.7,249.7,"已完工","该项目已完工。"]
[17,"大安市2022年小额贷款贴息","乡村振兴局",300,214.9152,"已开工","已进行第一批贴息，剩余部分将于2023年1月1日公示后进行贴息。"]
[18,"2021年项目质保金",null,1000,486.1746,"已开工","正在陆续发放已到期项目质保金。"]
[19,"2022年雨露计划补贴",null,97.5,92.7,"已完工","该项目已完工。"]
[20,"安广镇农产品冷链仓储建设项目","安广镇",310,310,"已完工","该项目已完工。"]
[21,"安广镇“千村示范”农村基础设施建设项目",null,205.5,205.5,"已完工","该项目已完工。"]
[22,"安广镇农村基础设施建设项目",null,590.96,590.96,"已完工","该项目已完工。"]
[23,"叉干镇三八村养殖小区产业路建设项目","叉干镇",135,135,"已完工","该项目已完工。"]
[24,"叉干镇“千村示范”农村基础设施建设项目",null,200,200,"已完工","该项目已完工。"]
[25,"叉干镇“千村示范”农村基础设施建设项目（二）",null,249.54,249.54,"已完工","该项目已完工。"]
[26,"大赉乡农村公路建设项目配电线路改迁工程","大赉乡",156.6,156.6,"已完工","该项目已完工。"]
[27,"丰收镇“千村示范”农村基础设施建设项目","丰收镇",100,100,"已完工","该项目已完工。"]
[28,"丰收镇“千村示范”农村基础设施建设项目（二）",null,99.955,99.955,"已完工","该项目已完工。"]
[29,"丰收镇2022年农村基础设施建设项目",null,569.6,569.6,"已完工","该项目已完工。"]
[30,"海坨乡“千村示范”农村基础设施建设项目","海坨乡",100,100,"已完工","该项目已完工。"]
[31,"海坨乡“千村示范”农村基础设施建设项目（二）",null,99.98,99.98,"已完工","该项目已完工。"]
[32,"乐胜乡“千村示范”农村基础设施建设项目","乐胜乡",259.83,259.83,"已完工","该项目已完工。"]
[33,"乐胜乡农村基础设施建设项目",null,903,903,"已完工","该项目已完工。"]
[34,"乐胜乡“千村示范”农村基础设施建设项目（二）",null,350,350,"已完工","该项目已完工。"]
[35,"联合乡“千村示范”农村基础设施建设项目","联合乡",100,100,"已完工","该项目已完工。"]
[36,"联合乡“千村示范”农村基础设施建设项目（二）",null,70,70,"已完工","该项目已完工。"]
[37,"红岗子乡马营子村棚膜示范园区建设项目","红岗子乡",1600,1600,"已开工","正在施工，工程形象进度46%，正在建设大棚主体，预计2023年5月完工。"]
[38,"红岗子乡农产品冷链仓储建设项目",null,1350,1350,"已开工","正在施工，工程形象进度70%，正在准备设备入场，预计2023年5月完工。"]
[39,"红岗子乡一心村农田改造提升项目",null,848.53,848.53,"已开工","正在施工，工程形象进度20%，正在进行土地平整、挖沟渠，12月份可完成今年建设任务。续建工程预计2023年5月初全部完工。"]
[40,"红岗子乡“千村示范”农村基础设施建设项目",null,100,100,"已完工","该项目已完工。"]
[41,"红岗子乡“千村示范”农村基础设施建设项目（二）",null,150,150,"已完工","该项目已完工。"]
[42,"大安市两家子镇同权村大挠子产业项目","两家子镇",770,770,"已完工","该项目已完工。"]
[43,"两家子镇“千村示范”农村基础设施建设项目",null,200,200,"已完工","该项目已完工。"]
[44,"两家子镇同富村农村公路建设项目",null,440,440,"已开工","已开工建设，已完成工程总量的30%，剩余工程量计划明年实施，预计2023年5月末完工。"]
[45,"大安市两家子镇同德村、同顺村“千村示范”农村基础设施建设项目",null,290,290,"已完工","该项目已完工。"]
[46,"两家子镇同乐村基础设施建设项目",null,360,360,"已完工","该项目已完工。"]
[47,"龙沼镇“千村示范”农村基础设施建设项目","龙沼镇",283.93,283.93,"已完工","该项目已完工。"]
[48,"舍力镇“千村示范”农村基础设施建设项目","舍力镇",399.76,399.76,"已完工","该项目已完工。"]
[49,"舍力镇民权村、庆新村排水工程",null,210,210,"已完工","该项目已完工。"]
[50,"烧锅镇乡“千村示范”农村基础设施建设项目","烧锅镇乡",100,100,"已完工","该项目已完工。"]
[51,"四棵树乡四棵树村狐貉养殖园区基础设施项目","四棵树乡",183.6,183.6,"已完工","该项目已完工。"]
[52,"四棵树乡“千村示范”农村基础设施建设项目",null,200,200,"已完工","该项目已完工。"]
[53,"四棵树乡“千村示范”农村基础设施建设项目（二）",null,189.0828,189.0828,"已完工","该项目已完工。"]
[54,"太山镇现代农业示范园区农产品冷链仓储建设项目","太山镇",350,350,"已开工","正在施工，工程形象进度39%,目前已完成钢构主体，准备做保温。预计2023年5月全部完工。"]
[55,"太山镇“千村示范”农村基础设施建设项目",null,220.52,220.52,"已完工","该项目已完工。"]
[56,"太山镇长春村渔猎小镇建设项目",null,300,300,"已开工","正在施工，工程形象进度32%,预计2023年6月全部完工。"]
[57,"新艾里乡富兴村农田打井上电工程","新艾里乡",233,233,"已完工","该项目已完工。"]
[58,"新艾里村“千村示范”农村基础设施建设项目",null,100,100,"已完工","该项目已完工。"]
[59,"新艾里乡“千村示范”农村基础设施建设项目（二）",null,49.96,49.96,"已完工","该项目已完工。"]
[60,"月亮泡镇农产品冷链仓储建设项目","月亮泡镇",1350,1350,"已开工","正在施工，工程形象进度45%，正在进行钢构建设，预计12月份主体完工。"]
[61,"月亮泡镇“千村示范”农村基础设施建设项目",null,384.8,384.8,"已完工","该项目已完工。"]
[62,"月亮泡镇志发村“千村示范”农村基础设施建设项目",null,160,160,"已完工","该项目已完工。"]